WORKPLAN 2004/2005: OFFICE OF THE PUBLIC SERVICE COMMISSION

| Key Performance Area | Objective | Indicators | Output | Commencing Date | Completion Date |
| --- | --- | --- | --- | --- | --- |
| GOVERNANCE MONITORING Public Service M&E Systems | Regular useful and timely information provided to relevant stakeholders on public administration and governance frameworks. | Timely collection and presentation of quality, relevant information and recommendations to stakeholders. Executives and Legislatures are informed of the state of the Public Service and service delivery issues. Recipients are provided with advice. Departmental monitoring reports generated. Compliance monitoring reports generated. Regulatory compliance evaluations undertaken and reports produced. Monitoring Reports on the implementation of the recommendations of the OPSC. | Approved M&E Report for the 2003 cycle. | Ongoing | December 2004 |
|  |  |  | Conduct an M&E system evaluation of at least 5 national and 6 provincial departments and deliver a least 11 draft reports. | June 2004 | March 2005 |
|  |  |  | Conduct an evaluation of Departmental M&E systems. | March 2004 | November 2004 |
|  |  |  | State of the Public Service Report | June 2004 | December 2004 |
| Compliance Monitoring |  |  | Monitor the verification of qualifications by Departments (levels 9 – 10). | March 2004 | December 2004 |
|  |  |  | Assessment of the corruption prevention plan in the Department of Justice – Master’s Office. | March 2004 | June 2004 |
|  |  |  | Monitor the implementation of the Commission’s recommendations. | Ongoing | Reports in September 2004 and February 2005. |
|  |  |  | Evaluate the implementation of the Administrative Justice Act. | April 2004 | October 2005 |
| Carry Over Projects |  |  | Investigation into allegations of maladministration in the Department of Transport, KwaZulu/Natal. | June 2003 | June 2004 |
|  |  |  | Investigation into allegations of corruption and maladministration in the Department of Home Affairs, KwaZulu/Natal, Durban. | November 2003 | June 2004 |
|  |  |  | Management Intervention in Northdale Hospital in KZN. | February 2004 | October 2004 |
| LEADERSHIP AND PERFORMANCE IMPROVEMENT HoD Performance Management Monitoring | To promote a high standard of public service leadership and to promote improved public service delivery. | Timely collection and presentation of quality, relevant information to stakeholders complete with clear and useful recommendations. Performance and standard of leadership improved. Executives and legislatures are informed of the state of service delivery. Recipients of advice are satisfied with the information and analysis provided to them. Recommendations are implemented. | The HoD evaluation process managed. | April 2004 | March 2005 |
|  |  |  | Monitoring of departmental performance. | April 2004 | March 2005 |
|  |  |  | The implementation of the HoD evaluation framework monitored and evaluated. | June 2004 | March 2005 |
|  |  |  | HoD's Perfromance Agreements (PAs) monitored and evaluated. | April 2004 | November 2004 |
| Program Evaluation |  |  | Evaluate the Poverty Relief Programme (PRP). Phase I: Audit of existing programs. | July 2004 | March 2005 |
| Carry Over Projects |  |  | Management of the HoD Evaluation process evaluated. | April 2003 | June 2004 |
| SERVICE DELIVERY AND QUALITY ASSURANCE Quality Assurance | Regular useful and timely information provided to stakeholders on service delivery and quality assurance. | Executive and legislatures are informed about the state of service delivery. Recipients of advice are satisfied with the information and analysis provided to them. Recommendations are implemented. | Evaluate compliance with the Batho Pele principle of Access in the Public Service. | June 2004 | June 2005 |
|  |  |  | Evaluate compliance with the Batho Pele principle of Redress in the Public Service. | June 2004 | June 2005 |
| Participatory Evaluations |  |  | Citizen Satisfaction Survey in the Economic & Infrastructure services. | June 2004 | March 2005 |
|  |  |  | 18 Citizens’ Forums across nine provinces. | May 2004 | May 2005 |
|  |  |  | Evaluate service standards in the departments falling under Justice and Protection Services, Financial and Administration Service, Central Government Administration and Social Services sectors. | January 2004 | December 2004 |
|  |  |  | Citizen Satisfaction Survey conducted in the Justice and Security Services sector. | November 2003 | August 2004 |
| Carry Over Projects |  |  | Provide assistance to the Chief State Law Adviser on the possible conversion of the Office. | December 2003 | May 2004 |
|  |  |  | Develop and popularize Good Practice Guides on Police Stations Management. | November 2003 | August 2004 |
|  |  |  | Publish guide on performance management in welfare departments. | May 2004 | July 2004 |
|  |  |  | Publish guide on performance management in hospitals. | May 2004 | August 2004 |
|  |  |  | Develop service delivery guides for critical services in Government. | September 2003 | June 2004 |
|  |  |  | Development of a Guideline for School District Management. | April 2004 | June 2004 |
|  |  |  | Citizen Satisfaction Survey: Northwest Province | Decision on future of project pending. | Decision on future of project pending. |
|  |  |  | Monitoring and Evaluation of the Distribution of Learner Support Material. | May 2004 | August 2004 |
| 4. CHIEF DIRECTORATE: LABOUR RELATIONS IMPROVEMENT | To enhance public service labour relations and management practices | Reports with recommendations produced. Extent to which recommendations are implemented. Best practices are identified and promoted Legal support accepted. Number, quality and timeliness of reports | Grievances lodged investigated | Ongoing | Ongoing |
|  |  |  | Complaints lodged investigated. | Ongoing | Ongoing |
|  |  |  | Review of the labour relations case management system. | 1 April 2004 | 31 March 2005 |
|  |  |  | Legal support service rendered to the PSC and the Office | Ongoing | Ongoing |
|  |  |  | Launch of the Complaints Rules | 1 April 2004 | 30 June 2004 |
|  |  |  | Development and promotion of Guidelines in respect of the new Grievance Rules. | 1 January 2004 | 30 April 2004 |
|  |  |  | Verification of the implementation of the grievance procedure as contained in Government Gazette number 25209. | 1 April 2004 | 31 March 2005 |
|  |  |  | A review on the handling of grievances and complaints undertaken through comparative study. | 1 April 2004 | 31 March 2005 |
|  |  |  | Continuous involvement/ observation in the PSCBC/ NEDLAC and the Labour Relations Forum for National Departments and the Provincial Administration: Eastern Cape. | Ongoing | Ongoing |
|  |  |  | Preparatory work towards the establishment of a Labour Bulletin. | 1 April 2004 | 31 March 2005 |
|  |  |  | Investigation into the effectiveness of Employee Assistance Programmes (from 2003/ 2004). | 12 June 2003 | 30 April 2004 |
|  |  |  | Ad hoc projects executed-including cross-functional investigations. | Ongoing | Ongoing |
| 5. CHIEF DIRECTORATE: PUBLIC ADMINISTRATION INVESTIGATIONS | To undertake audits and investigations into public administration practices | Reports with recommendations produced Recommendations implemented Best practices are identified and promoted Number, quality and timeliness of reports | Development of investigative methodology, practice guidelines and systems for forensic investigations. | April 2004 | December 2004 |
|  |  |  | - Guidelines on conducting investigations. |  |  |
|  |  |  | - Format for reporting. |  |  |
|  |  |  | Focused development and training program for staff in forensic investigations. | April 2004 | March 2006 |
|  |  |  | Investigations on own accord identified, including: | Ongoing |  |
|  |  |  | - Investigate nepotism/ favouritism in recruitment & selection. |  |  |
|  |  |  | - Misrepresentation of qualifications on a cross-functional basis (as arise out of monitoring) |  |  |
|  |  |  | Investigation of hotline cases emanating from the national anti-corruption hotline system |  |  |
|  |  |  | Responding to requests for focused investigations at the instance of: | Ongoing |  |
|  |  |  | - EA’s and HOD’s |  |  |
|  |  |  | - Anonymous/ whistle blowing |  |  |
|  |  |  | Provide forensic expertise, analysis and advice in order to ensure that a forensic and auditing function is rendered in respect of investigations undertaken. | Ongoing |  |
|  |  |  | Report on financial misconduct. | Ongoing |  |
| 6. CHIEF DIRECTORATE: PROFESSIONAL ETHICS AND HUMAN RESOURCE REVIEWS | To conduct training on ethics and anti-corruption measures Participate in cross-functional investigations Develop resource material for use by departments Advise departments on implementation and application of the code of conduct for the public service Conduct research and facilitate the production of reports on agreed upon topics Produce reports after investigations and inspections Provide professional advice on strategic human resource issues | Reports with recommendations produced Extent to which recommendations are implemented Best practices are identified and promoted Legal advice Number, quality and timeliness of reports | Review of gender main streaming initiatives by departments at national and provincial level. | 1 April 2004 | 30 November 2004 |
|  |  |  | Evaluation of the capacity of the public service at middle management level focusing on vacancy rates, competency levels etc. | 1 July 2004 | 31 March 2005 |
|  |  |  | Investigate the capacity of the HIV/AIDS framework to absorb the potential impact of HIV/AIDS on the human resources of the public service (Employee Assistance Programmes on HIV/AIDS, sickness and ill-health retirement) | 1 May 2004 | 28 February 2005 |
|  |  |  | Reporting to requests for focused investigations into specified human resource practices in departments. | To be determined in line with the nature of requests received | To be determined in line with the nature of requests received |
|  |  |  | Promotion of Code of Conduct and Anti-Corruption measures through training workshops. | Ongoing | Ongoing |
|  |  |  | Manage Asset Register | Ongoing | Ongoing |
|  |  |  | Produce Anti-Corruption promotional material | Ongoing | Ongoing |
|  |  |  | Provide secretarial service to National Anti-Corruption Forum | Ongoing | Ongoing |
|  |  |  | Conduct research on Conflict of Interest in order to contribute to a regulatory framework | July 2004 | Nov 2004 |
|  |  |  | Manage National Anti-Corruption Hotline. | June 2004 | Ongoing |
| 7. CHIEF DIRECTORATE: CORPORATE SERVICES AND REGIONAL LIAISON |  |  |  |  |  |
| Financial Management | Improve financial and management accounting Improve project budgeting and costing | Improved cashflow management | Implement changes to financial reporting format to economic report format | 1 April 2004 |  |
|  |  |  | Training of officials as a result of the possible implementation of accrual system of accounting | As determined by National Treasury |  |
|  |  | Improved budget management and reduction in incidences of budget overruns on projects | Focus on Fixed Assets management as a result of the possible changes to accounting policy | 1 July 2004 |  |
|  |  |  | Focus on improved overall financial and budgetary management within the Office to enhance financial forecasting and cash flow management | 1 July 2004 (SCOA code structure – 1 April 2004) |  |
|  |  |  | Introduction of project budgeting and costing which incorporates personnel expenditure |  |  |
| Human Resource Management | Improve HR utilization, management and development | More focused training programme | Revised and finalized HRD Plan | 1 April 2004 |  |
|  |  | Reduction in staff turn over | Finalised retention strategy and policy. | 1 April 2004 | June 2004 |
|  |  |  | Internship programme and learnerships | 1 May2004 | Ongoing |
|  |  | Social and/or work related problem successful resolved | Service provider appointed for referrals Finalised EAP policy | 1 June 2004 | Ongoing |
|  |  |  | EPMIS monitoring and evaluation Finalised special programmes and polices Finalised implementation of the Grievance Rules and Procedures | 1 April 2004 |  |
| Procurement and Logistical Services | Implement supply chain management transformation and improvement in procurement turnaround times | Reduced procurement turnaround time | Management of the increased procurement delegations |  |  |
|  |  | Adherence to procurement prescripts Increased security over incoming and outgoing mail | Management of the implications of the disbandment of the State Tender Board and supply chain management reforms Review of the OPSC Procurement Policy Review and implementation of the OPSC Travel and Subsistence Policy Review and implementation of the OPSC Postal Service Policy | 1 April 2004 1 April 2004 1 April 2004 1 April 2004 | 31 March 2005 |
|  |  | Improved management of incoming and outgoing mail | Operationalising the Office’s Procurement Policy and the promotion of the effective utilization of the web-based supplier database | Ongoing |  |
|  |  | Increase in BEE procurement | Focus on BEE and enhancement of database in this regard Review of the OPSC filing system to line with the Office’s new structure | 1 April 2004 1 June 2004 | Ongoing 30 Nov 2004 |
| Group Information Technology | Improve utilisation of IT infrastructure and reliability thereof | 99% network uptime | Implementation of Information security policies and systems | May 2004 | Ongoing |
|  |  | Increased utilization of IT as a work facility | Promote user training at colleague level | June 2004 |  |
|  |  | Increased IT literacy | Increase capacity for support services as well as utilisation of IT infrastructure | July 2004 | January 2005 |
|  |  |  | Management of exposure to litigation arising out of installation and use of illegal software on Offices PCs | September 2004 | Ongoing |
|  |  |  | Effective management of Service Level Agreements with SITA | April 2004 | March 2005 |
| Security Services | Improve security, health and safety within the OPSC’s premises | Reduced incidences of security breach | Implementation of OPSC Security Policy and Contingency Plan | 1 May 2004 | Ongoing |
|  |  |  | Improvement of physical security at Head Office and Regional Offices | Ongoing |  |
|  |  |  | Monitor health, safety and security regulations compliance | Ongoing |  |
|  |  |  | Focus on obtaining security clearances for all affected officials | Ongoing |  |
| Communication and Information Services | Increase level of awareness of the PSC and its products | Library products and services accessible on-line | Arrange availability and accessibility of IRC products and services online | Ongoing linked to IKM | Ongoing linked to IKM |
|  |  | Effective implementation of the Communication strategy | Annual review of the PSC’s communication strategy and development of implementation plan in this regard | April 2004 | May 2004 |
|  |  | Two issues of the magazine published | Bi-annual production and publishing of the PSC’s external magazine | June 2004 | Dec 2004 |
|  |  | Corporate Video developed | Development of corporate video | April 2004 | Dec 2004 |
|  |  | Effective implementation of the Communication Strategy | Ongoing maintenance of appropriate corporate identity and protocols | Ongoing | Ongoing |
|  |  | Media briefing lunches held | Improve media relations by hosting media briefing lunches | June 2004 | Nov 2004 |
|  |  | Utilisation of Intranet service promoted | Promote effective utilization of the Intranet | Ongoing | Ongoing |
|  |  | Information Survey conducted | Conduct survey on the level of awareness with regard to the PSC and its mandate | May 2004 | July 2004 |
|  |  | Annual Report published | Compilation of the Annual Report | April 2004 | August 2004 |
|  |  | Internal newsletter distributed online to staff every 2nd month | Bi-monthly production and publishing of Internal Electronic Newsletters – Izwi |  |  |
|  |  | Government communicators updated on PSC products and programmes | Participation in the inter ministerial and inert departmental activities | Ongoing | Ongoing |