BROAD STRATEGIC OBJECTIVES OF THE CGE

A. EXTERNAL BENEFICIARIES AND STAKEHOLDER

| STRATEGIC OBJECTIVE | MEASUREMENT | INDICATOR | 2006/7 | 2007/8 | 2008/9 |
| --- | --- | --- | --- | --- | --- |
| To provide a range of quality and accessible services | •Assess access • Level of awareness (%) demonstrated through surveys • Increased level of satisfaction | 1 in each year of plan Increase by 5% on base by 2009 Increase by 5% on baseline by 2009 | Develop services, access and stakeholder satisfaction: • Establish stakeholder satisfaction baselines • Strengthen outreach service in all provinces | Increase stakeholder satisfaction by 2% on baseline •Review outreach services | Develop services, access and stakeholder satisfaction •Review training services • Increase stakeholder satisfaction by 3% on baseline |
| To influence legislation and policies to be gender sensitive | • Impact of major policy submissions •Key gender quality issues addressed, with agreed performance indicators met, in defined public policy areas: (List key issues each year + expected outcome) | 75% of submissions to policies and legislation accepted Agreed, accepted and disseminated to all key stakeholders submitted on time | Respond to all legislation and relevant policy consultations Agree & promote recommendations on the following Acts and Policies; (list three) | Respond to key policy consultations Agree & promote recommendations on the following Acts and Policies; (list three) | Respond to key policy consultations Agree & promote recommendations on the following Acts and Policies; (list three) |

B. FINANCE

| STRATEGIC OBJECTIVE | MEASUREMENT | TARGETS | 2006/7 | 2007/8 | 2008/9 |
| --- | --- | --- | --- | --- | --- |
| To make effective, efficient and strategic use of Our resources. | Financial audits• Budgeting | Unqualified audit report to be issued by the Office of the Auditor-General Budget (including departmental budgets) agreed on and submitted before the start of each financial year | Unqualified audit report To be submitted to plenary and approved by March in the preceding year | Unqualified audit report To be submitted to plenary and approved by March in the preceding year | Unqualified audit report To be submitted to plenary and approved by March in the preceding year |
| To control costs | Expenditure against budget – | Negative variance of no greater than 2% (Over expenditure). Positive variance of no greater than 10% (Under expenditure) | Operate within agreed budget, implementation of an early warning system and cash management system | Operate within agreed budget | Operate within agreed budget |
| Reporting to donors | Accurate and timely reporting to donors | All donor funding reporting to be done as per donor funding contract | Timely and accurate reporting to donors | Timely and accurate reporting to donors | Timely and accurate reporting to donors |

C. PROCESSES

| STRATEGIC OBJECTIVE | MEASUREMENT | TARGETS | 2006/7 | 2007/8 | 2008/9 |
| --- | --- | --- | --- | --- | --- |
| Strengthen operational systems to be more efficient, effective, economic and transparent | Performance management systems Financial controls and procedures Supply chain management and Management Information Systems (MIS) | Implemented policy and functioning performance management system in place No reports of lack of controls within the significant section of the Auditor-General’s management letter. No reports of lack of controls within the significant section of the Auditor-General’s management letter not reported in management All key strategic areas monitored via a functioning MIS system – reports on a monthly basis | Documentation Approval of policy by July 2006. Implementation by October 2006 and performance review against strategic objective of the CGE and individuals Review of internal audit reports to ensure proper financial measures are in place Review and maintenance of system Design of detailed system, implementation of interim management system | Performance review against strategic objective of the CGE and individuals Review of all financial policies to ensure compliance with PFMA and Treasury regulation, internal audit on financial systems Review and maintenance of system Implementation of Electronic MIS system, | Performance review against strategic objective of the CGE and individuals Monitoring of all financial systems and implementation of new legislation. Review and maintenance of system Monitoring and review of MIS system |
| Periodically Induct and refresh staff on existing policies and systems | Reports on sessions held | 90% achievement of compliance to policies and systems within three years | Induction programme for new staff and update session for all staff | Induction programme for new staff and update session for all staff | Induction programme for new staff and update session for all staff |

D. LEARNING AND GROWTH

| STRATEGIC OBJECTIVE | MEASUREMENT | TARGETS | 2006/7 | 2007/8 | 2008/9 |
| --- | --- | --- | --- | --- | --- |
| To have staff numbers and required skill to deliver our Services. | Approved viable human resource plan Assessment of staff training needs Achievement of Personal development plans Reduced vacancy rate | Updated plan at the beginning of each financial year All staff assessed annually (90% achievement of personal development plans for staff and a 65% rate for the CGE) Average rate of vacancies vs. approved structure of not more than 10% per year (Monitored monthly) | Deliver training on corporate governance for Commissioners Develop and maintain staff expertise through development personal plans Detailed recruitment plan and strategy of appointment. | Review appraisal Scheme and align training needs with revised appraisal process Undertake training needs assessment Detailed recruitment plan and strategy of appointment. | Review appraisal scheme and align training needs with revised appraisal process Undertake training needs assessment Detailed recruitment plan and strategy of appointment. |

PLAN OF ACTION for 2006/2007

DEPARTMENT OF PUBLIC EDUCATION AND INFORMATION

| OBJECTIVE | ACTIVITY | RESULTS / OUTPUT | INDICATORS | TIME FRAME | Complimentarity of departmental services |
| --- | --- | --- | --- | --- | --- |
| Develop, Conduct and Manage Education and Information Programmes | Education Programmes |  |  |  |  |
|  | Development of Education Material Popularise Beijing platform of Action & the CEDAW | High quality educational material CEDAW + Beijing platform of action Well informed communities about gender and gender equality. | Availability of educational material Availability of simplified versions of Beijing and CEDAW | April 2006 – March 2007 Feb – March 2007 | Research & Legal |
|  | Train the Trainers | Self confident and highly competent staff & partners | Trained trainers (Internal, EO’s) | February 2007 |  |
|  | Gender Training + Human Rights | Self confident, high productivity and highly competent staff | Trained CGE members | Ongoing | HR, Research & Legal |
|  | IT Training | Self confident, high productivity and high competency staff | Trained end users | ongoing | HR |
|  | Workshops (40 per province) [Equality Project] Poverty GBV Employment Equity Democracy Governance Citizenship Culture, Religion and tradition Maintenance Domestic Violence Recognition of Customary Marriages | Gender sensitive and gender aware communities | Completed workshops as planned Provincial / National calendar by April 2006 | April 2006 – March 2007 | Legal and research departments to inform the process about the state of equality courts in South Africa |
| Develop concept papers | Gender Dialogues (4 per Province) | Gender sensitive and gender aware communities (ID topics per province (16 days, 10 years etc to be included)) | Completed dialogues as planned – (ID objectives, report to inform future CGE strategies) Provincial / National calendar by April 2006 – Include measures | April 2006 – March 2007 | Crucial research and legal processes that requires consultation top be included in the planning |
|  | Campaigns (4 per province) 16 Days of no violence against women and children 10th anniversary of the constitution 50th anniversary of the women’s march | Gender sensitive and gender aware communities (ID topics per province(16 days, 10 years etc to be included) | Completed campaigns as planned - (ID objectives, report to inform future CGE strategies) Provincial / National calendar by April 2006– Include measures | April 2006 – March 2007 | Crucial research and legal processes that requires consultation top be included in the planning |
|  | Provincial Widows Conferences (requires external funding () | Gender sensitive and gender aware communities | Completed conferences as planned | June 2006 – Sept 2006 | Provincial hearing on widows to be done by research department |
|  | National Widows Conference (requires external funding () | Gender sensitive and gender aware communities | Completed conferences as planned | March 2007 |  |
|  | Calendar of events | Detailed national / provincial calendar | Completed, agreed communicated | April 2006 |  |
|  | CGE 10 years | Plan of action + Budgets | Completed, agreed communicated | June 2006 | All parties, Chair, CEO, Legal, Research, Finance |
|  | Gender Education at Schools | Gender sensitive and gender aware learners | Completed dialogues as planned | April 2006 – March 2007 | Crucial research and legal processes that requires consultation top be included in the planning |
|  | Situational Analysis (Conducted at every Education intervention) | Compilation and analysis of workshop questionnaires | Available data / information | Ongoing | To be done jointly with the research department |
|  | Information Programmes |  |  |  |  |
|  | Publications (Content Development, Printing and Distribution) | High quality publications that are in demand. | Availability of Publications in all CGE offices ready for distribution. | Ongoing |  |
|  | Installation of Telephones Audio on Hold | Efficient Public Relations for the CGE | All CGE offices have audio on hold | May 2006 |  |
|  | Establishment of CGE National Archive | Efficient information and knowledge management | Availability of CGE National Archive | June 2006 |  |
|  | Establishment of Intranet Service, Help Desk Service | Efficient information management and IT problems management | Availability of Intranet and Help Desk Service | June 2006 |  |
|  | Establishment of Video Conferencing & Establishment of Information Technology Infrastructure & Support | Satisfied end-users | Reliable, efficient and effective IT system | March 2006 & May 2006 |  |
|  | Establishments and Administration of Resource Centres /Information | Efficient information dissemination | Availability of Recourses Centres / Information Centres in Provinces | April 2006 – March 2007 |  |

COMMUNICATION STRATEGY

| Objective | Activity | Result/Output | Indicator | Time Frame | Complimentarity of departmental services |
| --- | --- | --- | --- | --- | --- |
| Develop and implement the Communication strategy of the Commission. Foster favourable relations with local and national media to receive optimal and positive reporting | Organise and co-ordinate editors’ breakfast | Gender sensitive editors. Accurate, informed and sensitive reporting of CGE issues in the media. | Increased number of gender stories | April 2006 – March 2007 | Commissioners and senior managers to play an active role in promoting the image of the CGE |
|  | Organise and Co-ordinate media/press briefing for provincial media | Awareness in provincial media about CGE work and gender sensitive reporters | Increased numbers of gender & CGE stories in provincial media | Ongoing |  |
|  | Prepare media statements and releases | Knowledge and awareness of key gender issues | Increased number of South Africans aware of the operations of the CGE | Ongoing |  |
|  | Updating Gender and Media directory | Gender balanced and unbiased stories from both women and men sources. | Increased number of women experts. Resource persons easily accessible. | September 2006 |  |
|  | Co-ordinate SABC radio slots | Number of slots or space per targeted media | Increased number of people is South Africa more informed about gender issues | April 2006- March 2007 |  |
|  | Media Advertising | Publicity for the CGE | Number of Print and broadcast advertisements about the CGE and its work | Ongoing |  |
| Increase awareness in local communities and its external target audiences | Partnerships with the Community Radio Sector | Programmes designed to promote CGE messages as well as provide interactive communication around issues of concern Engage listeners for the understanding of the CGE role and its objectives and to ensure full participation in the processes pr | Provide gender content for Programmes Facilitate a community radio sustainable gender equality programme | April 2006 – March 2007 |  |
| Promote awareness on the CGE and it’s work in all forms of the media | Newspaper supplements for targeted events/advertorials | Exposure of the CGE in print media around work that is being done for major events. Public will know more about the CGE and its work and also raise the profile of the organisation. Would be a good PR exercise. | Build interest and publicity on work done by CGE on major events – i.e. Women’s month&16 Days of Activism Campaigns | Ongoing |  |
|  | Regular contributions to selected Gender journals (e.g. Agenda, Succeed etc.) | Positive attitude toward the CGE | CGE profile increased | Ongoing | Processes to be inclusive of all CGE departments |
|  | Speech Writing and PowerPoint Presentations Development – (No resources currently () (To media) | High quality speeches and PowerPoint presentations | Archived speeches and presentations | Ongoing | With research |
|  | Administering Telephone & Walk-in Enquiries | Publicity for the CGE | Record of telephone enquiries and visitors | Ongoing |  |
|  | Development of Signage & Wall Images | Well marked and visible signage and good wall images | Availability of signage and wall images at / in CGE offices | May 2006 |  |
|  | Motion Advertising & Video Playing | Publicity for the CGE | Availability of motion advertising and video plays in CGE offices | May 2006 |  |
|  | Arrange and Manage Exhibitions | Publicity for the CGE | Availability of Exhibition Reports | Ongoing |  |
|  | Administering CGE Online Information & and Website | Efficient information dissemination | Online Information Directed to Relevant CGE Members. Updated Website | Ongoing |  |
|  | Advertising on radio newspapers and billboard | Positive attitude toward the CGE | CGE profile increased | For campaigns | Processes to be inclusive of all CGE departments |
|  | Building relationships with stakeholders (e.g. ASASA, SABC, journalist etc.) |  |  | Ongoing |  |

LEGAL DEPARTMENT

| Objectives | Activities | Responsibility | Time frame | Indicator |  |
| --- | --- | --- | --- | --- | --- |
| Investigate related complaints and issues of own accord and/or on receipt of complaints | Complaints processing and Management Law Clinic Status Submissions to Parliament Interaction with Parliament (National & Provincial ) International/Regional -Obtain membership/ observer status -compile CGE reports to CEDAW CRC CERD ACHPR | Legal Department HOD HOD/PO Chairperson, Commissioners and support staff | March 2006 September 2006 December 2006 December 2006 Weekly-Thursdays Needs based March 2006 July 2006 March 2006 Ongoing Ongoing December 2006 July 2006 September 2006 December 2006 March 2006 March 2006 | Policy on Complaints Management “Managing Complaints” Handbook Development of Software Archiving old complaints Legal Strategic intervention sessions internally and collaborative Litigating in the Equality Court Database of previously disadvantaged practitioners Concept Paper Meeting with Law Society /Chapter 9 Concept paper Drafting Submission Papers Meeting with Speakers, Committee Chairs, Gender friendly legislation Gender friendly legislation Domestication of CEDAW Ratification of CEDAW Protocol (individual complaints), CESCR Audit of Legislation S6 Committee/ Reference Group Observer Status UN Commission on Human Rights National Institutions of Human Rights-(OHCHR), ECOSOC ACHPR, ACRWC |  |

HUMAN RESOURCE SECTION

| Objective | Activities | Responsibility | Time Frame | Indicator |  |
| --- | --- | --- | --- | --- | --- |
| Recruitment | Recruitment & Selection | HR | April 2006 + Ongoing for remaining | Maintain a vacancy rate of below 10%, no positions to be vacant for longer than 2 months Gauteng and Mpumalanga Offices, and the Policy and Research Department to be fully staffed by end of April 2006 |  |
| Employment Equity Report | Employment Equity Committee | HR & EEC | October 2006 | Compliance with laws and regulation |  |
| Development of a viable HR system | Industrial Relations | HR | May 2006 | Resolved matters timeously |  |
| Team Building | Team Building | HR | Plan by August implemented by Feb 2007 | Compliance & Implementation of plan |  |
| PPR&R | Communication of the PPR&R | HR | April 2006 | A revised document to be ready by end of April 2006 |  |
| Induction of new staff | Introduction of mentoring and skills transfers | HR | Ongoing + Update by June 2006 | Induction programme for all new staff members |  |
| Internal HR Committee | Set up an internal HR Committee | HR | June 2006 | An HR committee to be in place by end of June 2006 |  |
| Performance Appraisals | Performance appraisal | HR | April & October of each year Training before contracts signed | Signed contracts and appraisals done timeously Develop and agreed with staff and managers trained. |  |
| Electronic Leave System | Leave Administration | HR | October 2007 | An electronic leave administration system to be in place by end of October 2007. | All departments |
| Relationship between HR and Labour Union | HR/Union relationship | HR | One meting per quarter | To have quarterly meetings with the union. |  |
| Skills Development Plan | 11. Skills Development Plan | HR | October 2006 | A report to be sent to DOL in October 2006. |  |

RESEARCH DEPARTMENT

| Objective | Activities | Time frame | Indicator | Results/Output | Linkages with CGE departments and provincial offices |
| --- | --- | --- | --- | --- | --- |
| MONITORING AND EVALUATION OF SOCIAL POWER CAPABILITIES AND ECONOMIC POWER OPPORTUNITIES | Project 1: Monitoring and evaluation of capabilities of specific groups to assert social, economic and cultural rights (Budget theme: Gender and Poverty) Conduct a situational analysis of the capacities and vulnerabilities of these groups Develop recommendations in terms of CGE mandate | Year 1: Widows Year 2: Girl children Year 3: People with disability | Samples of marginalized groups for assessment Database of capabilities and vulnerabilities | Report on the vulnerability and capacities of selected marginalized groups in society, plus recommendations on improved service delivery and policy to overcome gender-based discrimination | Legal dept to make submissions for law reform if required PEI to conduct workshops and campaigns in all Commissioners to undertake appropriate advocacy and lobbying Research officers in all provinces |
|  | Project 2: Monitoring and evaluation of gender perspectives in research, education and training (Budget theme: Gender, culture, religion) Survey gender in the curriculum in early childhood, primary, secondary and tertiary education and training institutions Survey gender research at tertiary education and research institutions | Year 1 Pilot phase Year 2 Implementation Year 3 Monitoring, evaluation and reporting | Gender analysis of a sample of curricula in all provinces Documentation of gaps and good practice Database of researchers and research topics | Quantitative and qualitative indicators for gender in the curriculum Database of gender research, researchers, degree and non-degree training programmes available Comprehensive report on the state of gender in the curriculum | Research Officers in all provinces |
|  | Project 3: Baseline research: Nationwide Gender opinion survey (Budget theme: Gender, culture, religion) Develop questionnaire Analyse and interpret data Develop recommendations for implementation of findings Disseminate information | 6 months | Countrywide survey | Database of findings Research report with recommendations | Research Officers in all provinces |
|  | Project 4: Gender and HIV/AIDS (Budget theme: Gender-based violence) Situational analysis of people living with HIV/AIDS | Year 1: Scoping Year 2: baseline research Year 3: follow-up study | Research proposal Database of findings | Comprehensive report with recommendations Strategy to address gender needs and concerns of people living with HIV/AIDS | Research Officers in all provinces |
| monitoring and evaluation of political power agency in public and private sectors and in civil society | Project 1: Auditing of gender mainstreaming in the public sector (Budget theme: Gender and Governance) Develop methodology and pilot a tool for assessment of gender transformation through gender mainstreaming policies, structures and mechanisms in a sample of government departments on national and provincial level, and in metros, districts and local municipalities | Continuous activity; at least 2 departments on national level and at least one provincial dept and one local government per provincial office per year | Manual and scorecard for monitoring Accessible database updated and statistics available | Report with findings and recommendations on gender mainstreaming in government departments and on national, provincial and local levels of government | Research officers in all provinces Gender mainstreaming information and training to be provided by PEI as requested by respondents |
|  | Project 2: Auditing of constraints and capacities of National Gender Machinery (Budget theme: Gender and Governance) Survey the capacity of GFPs to implement gender policy to bring about transformation of gender relations in government | Continuous | Data collection instruments Database of findings | Comprehensive report on the capacity of GFPs and gender structures to implement gender policy | Research officers in all provinces |
|  | Survey initiatives by the Donor Community to promote gender equality Survey implementation of gender programmes in civil society | October – December 2006 |  | Report on the level of gender awareness among the donor community and civil society organizations | Research officers in all provinces |
|  | Project 3: Auditing of sexism and gender-based discrimination in the private sector (Budget theme: Gender and governance) Develop a tool for identification of sexism and gender-based discrimination Draw a sample of private and public sector organisations Send out questionnaires and capture responses | April 2006 – March 2007 | Comprehensive measuring instrument developed and administered Database of information available | Report with findings and recommendations on the identification and elimination of sexism and gender-based discrimination in private and public sector organisations | Manifestations of sexism in the private sector identified and reported to the Legal services dept for action; Information and training to be provided by PEI as requested by respondents as per the relevant province Research officers in all provinces |

# Footnotes

2006: Dept. of  Education; Dept. of Justice; Dept. of Minerals and Energy

2007: Department of Social Development; Dept. of Foreign Affairs; Dept. of Health

2008: Dept. of Provincial and Local Government; Dept. of Labour; Police Service