OSDP STRATEGIC PLAN – 2004 GOING FORWARD

| Measurable Strategic Objective: Implementation of government’s policies and programmes incorporate/inclusive of disability issues and people with disabilities |
| --- |
| Providing advice on implementation of policy frameworks for political principals, departments, provinces, local government and other role-players. | GLOBAL ACTIVITIES | GLOBAL OUTPUT | SUB-ACTIVITIES | DEADLINE |
|  | Definition of disability (DoH and Treasury) | Working definition of disability adopted and implemented | Task team meetings Write-up of definition/cabinet memo Table at cabinet meeting Adoption by Cabinet Final definition distributed to Departments, provinces and local government Awareness sessions with relevant groupings of public servants, DPOs and other role-players on definition | End of 2004 |
|  | Grants & Free Primary Healthcare Assessment tools (Social Services & DoH) | Assessment tool for pwds adopted and implemented | Task team meetings Write-up cabinet memo Table at cabinet meeting Adoption by cabinet Implementation of tool Awareness sessions on tool with relevant groupings of public servants, DPOs and other role-players | Mid 2005 |
|  | OSDP Inter-Provincial Forum (IPF) – reviewing provincial disability strategies | Provincial strategies aligned to political priorities, practical and relevant. Provincial strategies adopted and implemented in each province | Review existing strategies of each province Write-up recommendations on proposed alignment and adjustments Meet with/submit recommendations to each provincial head Adoption and implementation of strategy by each province | Mid 2005 |
|  | Education – piloting inclusive education, review meetings | Inclusive Education effectively implemented |  |  |
|  | Labour – learnerships, SETA’s, develop database of pwds seeking employment | Increase in learnerships to pwds and learnerships effectively managed |  |  |
|  | Finance – ensuring disability allocation in MTEF & MTEC | Disability allocations incrementally reflected in budget |  |  |
|  | Communications – radio production policy, MPCCs, other programmes for inclusivity of Disability issues | Policy inclusive of disability issues |  |  |
|  | Review of victim charter for inclusivity of disability issues | Victims Charter inclusive of disability issues |  |  |
|  | Review transport strategy for inclusivity of disability issues | Strategy inclusive of disability issues |  |  |
| Measurable Strategic Objective: Government’s monitoring and evaluation systems and processes include indicators and measures relating to improving the lives of pwds. |  |
| Monitoring & Evaluation (set indicators, establish systems and processes, monitor regularly, IDCC, IPF, etc) | Review of IDCC | Functional and effective departmental co-ordination, monitoring and evaluation structure functional and effective | Develop ToR for service provider to conduct review Appoint Service provider Provider conducts review and makes recommendations OSDP approves draft report and recommendations Table at GDC meeting Approved by GDC Table at relevant political meeting Approved at political level DG’s of each line department informed and briefed on revised structures Department’s appoint representatives Revised structure implemented | End of 2004 |
|  | Set disability specific indicators in conjunction with PCAS and Departments | Measurable and tangible disability specific indicators for each line department, in line with political priorities | Write up disability specific indicators for each line department/sector Discuss and approve with each department and PCAS PCAS incorporates into its overall indicators and M & E system | Nov 2004 |
|  | Implement Presidency M & E systems and processes | OSDP’s M & E systems and processes aligned and functioning according to that of the Presidency | Meeting with PCAS on systems, processes and what is required of OSDP Review and adjustment of OSDP systems and processes to ensure alignment with PCAS Induct/brief OSDP staff on revised system and processes Implement revised system | Nov 2004 |
|  | OSDP Inter-Provincial Forum M & E reports and systems | Provincial OSDP’s produce qualitative reports that indicate progress and weaknesses on implementation and service delivery regarding disability issues | Assess strengths and weaknesses of current reports Develop draft report format that will address weaknesses Induct/brief/train provincial staff on writing qualitative and substantive reports Monitor and provide support on writing of reports |  |
| Measurable Strategic Objective: Increase in number of pwds productively engaged in the economy and contributing to country’s GDP |  |
| Economic Empowerment Programme | Appointment of contract staff to implement EEP | One project manager and one administrator appointed and functinioning | Develop Job Specs in conjunction with HR Advertise, shortlist, etc Conduct interviews and appoint staff | End of Jan 2005 |
|  | Development of strategy for programme. | Economic Empowerment strategy focusing on pwds | Consultative processes with DPOs and other role players Draft strategy developed and adopted by OSDP Draft strategy submitted for political approval and adoption Strategy implemented | July 2005 |
|  | Disability issues included in strategy of support for co-ops | PWDs benefit from implementation of co-op strategy | Meetings with Department of Agriculture/task team Write-up guidelines for strategy on inclusion of disability issues Submit to Department of Agriculture/task team Awareness sessions on strategy with relevant groupings of public servants, DPOs and other role-players | Determined by Department of Agriculture |
|  | Review of SMME framework to include disability issues and PWDS | Increase in number of SMME’s comprising of pwds accessing government support and services | Attend relevant meetings Write-up guidelines for strategy on inclusion of disability issues Submit to the Department/task team Awareness sessions on framework and support with relevant groupings of public servants, DPOs and other role-players | Determined by Department |
|  | Review of NEF products to include pwds | NEF financial and non-financial products accessible to pwds | Attend relevant meetings Write-up guidelines for strategy on inclusion of disability issues Submit to the Department/task team Awareness sessions on framework and support with relevant groupings of public servants, DPOs and other role-players | Determined by Department |
|  | Increase of learnerships | Increase in number of pwds accessing and placed in learnerships | Meetings with relevant SETAs Assisting the SETA’s, learnerhsip management agencies, DPO’s, other role players to identify pwd learners Advising SETA’s and/or management agencies on the learnership programmes Monitoring and evaluating implementation | End of 2005 |
|  | EPWP | PWDs actively participating in EPWP projects at local level | Participate in relevant meetings Identify opportunities for PWD participation and develop targets/quotas for this Assist Department, DPOs and other role players with identifying pwds for participation Monitoring and evaluating participation of pwds in EPWP projects. |  |
| Measurable Strategic Objective: Disability desks/focal points established and functioning effectively at provincial and local government spheres of government |  |
| Establishing Disability Desks at provincial and local government level | Propose and advise on structure in municipality | Disability Desks established at ??? number of municipalities according to proposed structure | Meetings with relevant municipalities Revise and amend proposed structure Distribute proposed structure to relevant municipalities | End of 2005 |
|  | Assist with appointments at local level | Staff appointed in disability desks at municipalities | Develop proposed generic job specs for staff Advise on advertisements, and appointments | Ongoing |
|  | Provincial level | Appropriate staff appointed in provincial OSDP offices | Develop proposed generic job specs Assist with advertisements and short-listing Participate in interview panels and appointment of staff | Ongoing |
|  | Consultations and strategic meetings with provinces and municipalities | Provincial and municipality work on disability aligned to political priorities | Convene/participate in meetings as required Review and advise on plans and strategies | Ongoing |
| Measurable Strategic Objective: Government officials have necessary capacity to implement disability related policies and programmes |  |
| Training Programmes (SAMDI Trainers, councilors, top managers, etc) | SAMDI training of public servants on disability issues and the INDS | Focal point staff and other relevant staff in each department at national, provincial and local level demonstrate thorough understanding of disability issues and the INDS | Regular meetings with SAMDI Review and assess SAMDI training materials Assist SAMDI with identifying participants for training courses Monitor and evaluate SAMDI training i.r.o. content, processes and impact |  |
|  | Internal capacity building of OSDP Staff | OSDP staff have required capacity to effectively implement OSDP activities | Meetings with individual staff members on their capacity needs Meeting with HR on appropriate capacity building interventions Appointment of external service provider if required Staff trained Monitor and evaluate impact of training and use of skills gained | End of 2005 |
|  | Support to academic institutions on disability studies | Courses, content and programmes offered by academic institutions relevant and appropriate | On request, review training materials academic institutions On request, participate in academic institutions training programmes | Ongoing |
| Measurable Strategic Objective: South Africa contributes to, delivers on regional, continental and international commitments |  |
| Participate in continental and international initiatives (Nepad, African Decade, UN, Bi-national and bi-lateral commissions, etc) | Proposed UN Convention | Convention adopted and implemented by member states | Convene SA task team meetings Coordinate SA’s input to the draft convention and its processes Lead SA delegation and represent SA government views at UN meetings Participate in UN established task teams Report to Sa government and other role-players on progress |  |
|  | Implementing SA Plan of the Decade | SA government deliver on African Decade goals and objectives | Revise SA implementation Plan Convene/establish relevant implementation structures/processes Facilitate implementation Monitor and Evaluate implementation Provide progress reports to African Decade Secretariat | 2009 |
|  | Implement SA Plan of Continental Plan | SA government deliver on Continental Plan goals and objectives | Establish links between continental and decade Plan Align implementation with African Decade implementation Facilitate implementation Monitor and Evaluate implementation Provide progress reports to relevant structures | 2009 |
|  | WBU Conference | Conference successful with clear, tangible outcomes and resolutions | Participate in planning meetings Assist with securing SA speakers Assist with logistical and other conference arrangements Host the conference Assist with development and distribution of Conference report | End of 2004 |
|  | Bi-nationals – AusAid, GoF, Danish Government | Funded projects successfully implemented and relationship between partner representatives positive | Regular meetings and reports to relevant representatives Representatives participate in and/or attend relevant evens, functions and activities | Ongoing |
|  | Relate ARCC resolutions and decisions to the NEPAD Secretariat | NEPAD Secretariat includes disability issues and the ARCC resolutions in its programmes and activities | Meeting with African Decade Secretariat to hand over responsibility Facilitate, if required, meeting between African Decade and Nepad Secretariats Attend meeting, if so required | September 2004 |
|  | Monitor work of African Decade Secretariat | African Decade Secretariat functioning effectively and delivering on goals and objectives | Represent the OSDP/SA government at board meetings Attend all Board meetings Review and advise on all documents, reports, plans, etc | Ongoing |
|  | Adhoc contributions to other continental initiatives e.g. training, conferences | Successful implementation and relevant content of such initiatives | On request. attend relevant meetings Review and advise on documents, materials, reports, etc | Ongoing |
| Measurable Strategic Objective: Stronger co-operative relationship between government, the private sector and other role-players in the disability sector |  |
| Providing assistance and management support to other institutions developing policy on disability issues (DPOs, strategic meetings, serving on project management boards, etc) | 1. Telkom Foundation | Institution functions effectively and their work incorporates disability issues within a human rights framework | Attend meetings Review and advise on documents, materials, reports, etc | Ongoing |
|  | 2. African Decade Board | As above | As above | Ongoing |
|  | 3. CAAC Board | As above | As above | Ongoing |
|  | 4. CSIR Board | As above | As above | Ongoing |
|  | 5. DPO’s (as requested) with specific focus on MDG’s | As above | As above as well as co-ordinate and facilitate DPO input into other processes and activities | Ongoing |
|  | 6. SAFCD | As above | As above | Ongoing |
|  | 7. Other role players | As above | As above |  |
| Measurable Strategic Objective: Effective and efficient management of the OSDP in line with public service and financial regulations |  |
| Effective and efficient management of OSDP (Organisational Development eg. OSDP bosberaad, HOP meetings, progress reports, etc) | Day-to-day strategic leadership, management support and direction | OSDP managed efficiently in line with public service and financial regulations and delivering on its core functions | Attend presidency snr management meetings as required Attend weekly GDC/HOP meetings OSDP Staff meetings Meetings with the Minister Meetings with other programmes / departments in The Presidency Individual meetings with OSDP staff members Write and/or edit progress reports for political principals, senior managers, donors, etc Prepare presentations/ speeches/papers, i.r.o. institutional representation of OSDP Evaluations of donor funded projects, IDDC work and other work progress and impact | Ongoing |
|  | Convening organizational development processes | OSDP managed efficiently in line with public service and financial regulations and delivering on its core functions | OSDP Strategic Planning sessions Staff development issues | Ongoing |
|  | Financial Management & Accounting | OSDP managed efficiently in line with public service and financial regulations and delivering on its core functions | Monthly income and expenditure accounts Consolidate monthly report into quarterly reports for funders Consolidate quarterly reports for annual report to funders Prepare MTEF budget (annual, 3 year cycle and one on amendments) Prepare and submit annual report to Presidency on donor expenditure Meetings with Auditors x 4 Work with auditors x 2 weeks | Ongoing |
|  | GDC | OSDP managed efficiently in line with public service and financial regulations and delivering on its core functions | Attend meetings Identify and implement issues that can be integrated Other tasks, on request and as relevant | Ongoing |
| Measurable Strategic Objective: Increased public awareness on disability issues |  |
| Awareness Raising Project (media campaign, visual arts, IDDP, etc) | 16 days of no violence against women and children | Campaign incorporates disability issues and is successfully implemented | Attend relevant meetings Review and advise on processes, activities, etc Implement tasks arising from meetings Review and advise on publicity, other documents, etc | Nov & December every year |
|  | IDDP, National Heritage, Womens Day, HIV/Aids Day, Youth Day, Children Days, Human Rights Day, Freedom Day, Reconciliation Day, Workers Day, Casual Day, Deaf Awareness Week, etc | Commemoration activities reflect disability issues and are successfully implemented | Co-ordinate and implement national IDDP campaign and activities Other commemorative days - attend relevant meetings Review and advise on processes, activities, etc Implement tasks arising from meetings Review and advise on publicity, other documents, etc | IDDP - Nov & December every year Other days – as per calendar |
|  | Generic Media Policy | Media sector adopts and implements generic media policy | Review of existing policies Drafting of generic policy Workshop with media representatives Policy adopted and implemented | End of 2005 |
|  | Radio, TV and newspaper Ads | Adverts on disability issues flighted thereby increasing public awareness | Develop ToR for service providers Convene and co-ordinate task team/steering committee meetings Appoint service providers Develop Ads Flight Ads Evaluate impact | End of 2005 |
|  | Visual Arts and Crafts | Exhibitions held and increased public awareness | Source exhibits Plan, including logistical arrangement for exhibitions Hold exhibitions | End of 2005 |
|  | Integrated Dance | Shows conducted and increased public awareness in selected schools | Convene and co-ordinate meetings with artists Plan, including logistical arrangements for shows Conduct shows | End of 2005 |
|  | Anthology of writing | Anthology published and distributed to libraries, etc | Source editor and publishers Design and layout Publish and distribute | End of 2004 |
|  | Media Toolkit | Toolkit published, distributed and being used by DPOs and government | Final Edit Design and Layout Printing and distribution | March 2005 |
|  | Disability Communication Strategy | OSDP adopts and implements a communication strategy | Develop draft strategy Present to OSDP OSDP adopts and implements | March 2005 |