DIHLABENG LOCAL MUNICIPALITY

SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN

For

2007/2008

SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN

(SDBIP)

LEGAL REQUIREMENTS CONSIDERED WITH THE DEVELOPMENT /

DESIGN OF A SDBIP

In terms of Section 53(1)(c)(ii) of the Municipal Management Act (MFMA) No. 56 of 2003, the “service delivery and budget implementation plan” is defined as a detailed plan approved by the mayor of the municipality for implementing the municipality’s delivery of municipal services and its annual budget and which must include :

- projections for each month of-

    - Revenue to be collected by source; and

    - Operational and capital expenditure by vote;

- Service delivery targets and performance indicators for each quarter; and

- Any other matters that may be prescribed and includes any revisions of such plan by the mayor in terms of section 54(1)(c)”

The SDBIP therefore seeks to focus the municipality on both financial and non-financial outcomes in order to ensure effective and efficient service delivery.  In terms of (c) above National Treasury has prescribed in terms of MFMA Circular No. 13 that ward information for expenditure and service delivery and a detailed capital works plan also be included as part of a municipality’s SDBIP.

The Local Government Municipal Systems Act 32 of 2000, and Local Government Municipal Planning and Performance Regulations, requires Local Government to:

- Develop performance management system;

- Set targets, monitor and review performance based on indicators linked to the IDP ;

- Publish an annual report on performance management for the Councillors, staff, the public and other spheres of government;

- Incorporate and report on a set of general indicators prescribed nationally by the Minister responsible for Local Government;

- Conduct an internal audit on performance before tabling the report;

- Have the annual performance report audited by the Auditor-General; and

- Involve the community in setting indicators and targets and reviewing municipal performance.

SECTION 1: LINK WITH THE IDP AND PERFORMANCE MANAGEMENT SYSTEM/SCORECARD

  - Description of the core functions of the municipality, based on its legislative mandate.

The municipality performs the following core functions:

| Category B functions | Category C functions | Provincial & National Competencies |
| --- | --- | --- |
| A | B | C |
| Air pollution Building regulations Bill boards and display of advertisements Storm water Trading regulations Cleansing Facilities, accommodation and burial of animals Fencing and fences Local sport facilities Municipal parks and recreation Municipal planning Municipal public transport Municipal roads Public places Street lighting Traffic and parking Licensing of dogs Local amenities | Refuse removal, dumps and solid waste Municipal roads Municipal airports Fire fighting Markets Cemeteries Municipal public works Electricity regulation Municipal health Storm water Potable water Sanitation Licensing/control of undertakings that sell food to the public | Libraries Housing |

All of the above functions are dispersed within the existing structure of the Dihlabeng Local Municipality.

The functions indicated under column B are functions which are legislatively allocated to a district municipality, but which may be adjusted in terms of the Municipal Systems Act. The functions indicated under column C are functions which are national and provincial competencies.

  - Summary of the core contents of the IDP.

The IDP has the following core contents contain:

- Vision for the municipality;

- Strategic focus areas;

- Long-term goals or outcomes for the community;

- Reference to alignment with national, provincial and district plans;

- Consideration of service delivery and funding of housing, health and transport, etc;

- Summary of the medium-term objectives or outputs;

- Reference to measurable performance objectives;

- Description of prioritization systems used for allocating resources to objectives;

- Amendments to the IDP;

- Reference to the consultative process undertaken to review the IDP; and Tables showing the link between the IDP and Budget”.

  - Link between the IDP & the SDBIP.

- The Integrated Development Plan (IDP) outlines how the challenges of sustainable development in a municipality are to be met through strategic interventions and service delivery over the five year period.

- The IDP is developed by the municipality in conjunction with the community, and a credible IDP must be supported by the realistic budget. The actual implementation of the IDP over a single financial year is given effect through the performance contracts of the Municipal Manager and Directors.

- The performance management system monitors actual performance against contractual obligations. The effective service delivery relies upon the IDP, the budget and the performance management system being closely integrated

1.4	Explanation of the structure of the SDBIP, based on an analysis of the structure of the IDP.

- What the above diagram illustrates is that the SDBIP contains information in regard to service delivery targets, performance indicators and revenue and expenditure.

- It is also important to note that the SDBIP is firstly informed by the IDP and Budget, secondly that the annual performance agreements/contracts of the Municipal Manager and Section 56 Managers must be influenced by the SDBIP and thirdly that in-year reporting (monthly and quarterly), and annual reporting should be done against the information contained in the approved SDBIP.

    - Institutional Scorecard

- The process of developing the SDBIP will be followed by the development of the Institutional Scorecard.

- The scorecard will measure performance on 8 National Key Performance Areas which are derived from DPLG Regulations as well as the Municipal priorities.

- The Five Years Local Government Strategic Agenda will also be integrated into the scorecard.

1.4	Strategic Key Performance Areas

- Service Delivery and Infrastructure

- Local Economic Development

- Municipal Financial Viability

- Municipal Transformation and Institutional Development

- Good Governance

1.4.1	Each Strategic Key Performance Area will be delivered upon by various directorates.

1.4.2	The scorecard will represent the consolidation of service delivery targets and performance indicators in a more detailed Directorate and Departmental SDBIP’s.

1.4.3	The focus in this SDBIP is both financial and non-financial measurable performance objectives in the form of service delivery targets and other performance indicators.

The municipal scorecard will be structured in terms of the Balanced Scorecard approach that incorporates the following perspectives:

- Customer Perspective : This perspective has Key Performance Areas that are externally focused and relate to service delivery to the community

- Internal Business Perspective: The Balanced Scorecard approach recognizes that for the municipality to achieve its targets in the Customer Perspective internal business process must be improved to ensure that the municipality also continues adding value to the community as its customers.

- Learning and Growth : This perspective is the enabler of all perspectives as it is meant to ensure that the organisational infrastructure is geared towards assisting the municipality to achieve its objectives as contained in the other perspectives

- Financial Perspective: Given the scarce resources at the disposal of the municipality, this perspective ensures that the municipality achieves results in an efficient manner through the minimization of costs as well as the maximum collection of revenue due to it.

1.5	The following are the main focus points for delivery prioritization

- Water Services and Sanitation

- Electricity and Energy

- Solid Waste Management

- Environmental health Management

- Roads, Rails Stormwater and Buildings

- Housing

- Urban Efficiency and Spatial Planning

- Community Parks, Sports and Recreation

- Economic Growth

- Poverty Alleviation

- Job Creation

- Financial Management

- Internal Audit procedures

- Organisational Development

- Employment Equity

- Skills Development

- Integrated Development Planning

- Performance Management System

- Public Participation and oversight

- Co-operative Governance

- Ward System

- Corporate Governance

SECTION 2: INSTITUTION-WIDE BUDGET PLAN

| Monthly Projections Revenue by Source |
| --- |
| SOURCE | Jul-07 | Aug-07 | Sep-07 | Oct-07 | Nov-07 | Dec-07 | Jan-08 | Feb-08 | Mar-08 | Apr-08 | May-08 | Jun-08 | Jun-08 |
|  | R'000 | R'000 | R'000 | R'000 | R'000 | R'000 | R'000 | R'000 | R'000 | R'000 | R'000 | R'000 | R'000 |
| Assessment rates | 4 377 837 | 4 377 837 | 4 377 837 | 4 377 837 | 4 377 837 | 4 377 837 | 4 377 837 | 4 377 837 | 4 377 837 | 4 377 837 | 4 377 837 | 4 377 837 | 4 377 837 |
| Electricity | 4 723 284 | 4 723 284 | 4 723 284 | 4 723 284 | 4 723 284 | 4 723 284 | 4 723 284 | 4 723 284 | 4 723 284 | 4 723 284 | 4 723 284 | 4 723 284 | 4 723 284 |
| Water | 3 238 104 | 3 238 104 | 3 238 104 | 3 238 104 | 3 238 104 | 3 238 104 | 3 238 104 | 3 238 104 | 3 238 104 | 3 238 104 | 3 238 104 | 3 238 104 | 3 238 104 |
| Sanitation | 1 926 502 | 1 926 502 | 1 926 502 | 1 926 502 | 1 926 502 | 1 926 502 | 1 926 502 | 1 926 502 | 1 926 502 | 1 926 502 | 1 926 502 | 1 926 502 | 1 926 502 |
| Refuse removal | 1 398 565 | 1398 565 | 1398 565 | 1398 565 | 1398 565 | 1398 565 | 1398 565 | 1398 565 | 1398 565 | 1398 565 | 1398 565 | 1398 565 | 1398 565 |  |
| Service Charges | 564 375 | 564 375 | 564 375 | 564 375 | 564 375 | 564 375 | 564 375 | 564 375 | 564 375 | 564 375 | 564 375 | 564 375 | 564 375 |
| Rent of Facilities and Equipment | 304 401 | 304 401 | 304 401 | 304 401 | 304 401 | 304 401 | 304 401 | 304 401 | 304 401 | 304 401 | 304 401 | 304 401 | 304 401 |
| Interest Earned Outstanding Debtors | 1 222 886 | 1 222 886 | 1 222 886 | 1 222 886 | 1 222 886 | 1 222 886 | 1 222 886 | 1 222 886 | 1 222 886 | 1 222 886 | 1 222 886 | 1 222 886 | 1 222 886 |
| Fines | 148 591 | 148 591 | 148 591 | 148 591 | 148 591 | 148 591 | 148 591 | 148 591 | 148 591 | 148 591 | 148 591 | 148 591 | 148 591 |
| Licenses and Permits | 316 | 316 | 316 | 316 | 316 | 316 | 316 | 316 | 316 | 316 | 316 | 316 | 316 |
| Grants | 7 162 552 | 7 162 552 | 7 162 552 | 7 162 552 | 7 162 552 | 7 162 552 | 7 162 552 | 7 162 552 | 7 162 552 | 7 162 552 | 7 162 552 | 7 162 552 | 7 162 552 |
| DORA | 6 734 335 | 6 734 335 | 6 734 335 | 6 734 335 | 6 734 335 | 6 734 335 | 6 734 335 | 6 734 335 | 6 734 335 | 6 734 335 | 6 734 335 | 6 734 335 | 6 734 335 |
| Other | 732 908 | 732 908 | 732 908 | 732 908 | 732 908 | 732 908 | 732 908 | 732 908 | 732 908 | 732 908 | 732 908 | 732 908 | 732 908 |

| Monthly Projections Expenditure by Source |
| --- |
| SOURCE | Jul-07 | Aug-07 | Sep-07 | Oct-07 | Nov-07 | Dec-07 | Jan-08 | Feb-08 | Mar-08 | Apr-08 | May-08 | Jun-08 | Jun-08 |
|  | R'000 | R'000 | R'000 | R'000 | R'000 | R'000 | R'000 | R'000 | R'000 | R'000 | R'000 | R'000 | R'000 |
| Salaries, Wages & Allowances | 9 436 744 | 9 436 744 | 9 436 744 | 9 436 744 | 9 436 744 | 9 436 744 | 9 436 744 | 9 436 744 | 9 436 744 | 9 436 744 | 9 436 744 | 9 436 744 | 9 436 744 |
| General Expenses | 8 566 382 | 8 566 382 | 8 566 382 | 8 566 382 | 8 566 382 | 8 566 382 | 8 566 382 | 8 566 382 | 8 566 382 | 8 566 382 | 8 566 382 | 566 382 | 8 566 382 |
| Repairs & Maintenance | 850 518 | 850 518 | 850 518 | 850 518 | 850 518 | 850 518 | 850 518 | 850 518 | 850 518 | 850 518 | 850 518 | 850 518 | 850 518 |
| Capital Charges | 879 583 | 879 583 | 879 583 | 879 583 | 879 583 | 879 583 | 879 583 | 879 583 | 879 583 | 879 583 | 879 583 | 879 583 | 879 583 |
| Contribution to Capital Expenditure | 4 465 750 | 4 465 750 | 4 465 750 | 4 465 750 | 4 465 750 | 4 465 750 | 4 465 750 | 4 465 750 | 4 465 750 | 4 465 750 | 4 465 750 | 4 465 750 | 4 465 750 |  |
| Contributions to Reserves | 1 821 715 | 1 821 715 | 1 821 715 | 1 821 715 | 1 821 715 | 1 821 715 | 1 821 715 | 1 821 715 | 1 821 715 | 1 821 715 | 1 821 715 | 1 821 715 | 1 821 715 |

SECTION 3: PERFORMANCE ASSESSMENT

The Planning and Performance Regulations, 2001 requires quarterly performance assessment through the PMS of municipalities. The following performance assessment template has been developed to match the requirements of MFMA Circulars Nos. 13 and 12 with that requirement of the Regulations.

3.1	SERVICE DELIVERY PERFORMANCE

- MFMA Circular No. 13 describes the SDBIP as “… a management, implementation and monitoring tool”. The Circular emphasizes the fact that the SDBIP must be used as a monitoring tool and that quarterly performance reviews must be done to enable quarterly and mid-year reporting regarding operational performance of the municipality, and also as a tool to assess the performance of senior managers on a quarterly basis.

- The following format will therefore be used to quarterly review performance in terms of the key performance indicators and key performance targets exposed above:

QUATERLY PROJECTIONS FOR SERVICE DELIVERY TARGETS AND OTHER PERFORMANCE INDICATORS

DEPARTMENT:	CORPORATE SERVICES

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Vote | Project | Budget | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |
| Support Services | Upgrading of Council Facilities and Offices | 113 415 000 | 0 | 28 353 750 | 0 | 0 | 28 353 750 | 0 | 0 | 28 353 750 | 0 | 0 | 28 353 750 | 0 |
| HRD Skill Dev | Learnership Launch | 450 000 | 0 | 50 000 | 0 | 140 000 | 0 | 0 | 60 000 | 0 | 50 000 | 0 | 0 | 0 |
|  | Skills Programmes | 810 000 | 0 | 202 500 | 0 | 202 500 | 0 | 0 | 205 500 | 0 | 0 | 0 | 205 500 | 0 |
|  | Training Committee Workshop | 10 000 | 0 | 0 | 0 | 10 000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Training Mentors/Assessors | 6 000 | 6 0000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Labour Relations Training | 30 000 | 0 | 15 000 | 0 | 0 | 0 | 0 | 0 | 15 000 | 0 | 0 | 0 | 0 |
|  | Employee Wellness | 200 000 | 0 | 80 000 | 0 | 80 000 | 0 | 0 | 20 000 | 0 | 0 | 20 000 | 0 | 0 |

QUATERLY PROJECTIONS FOR SERVICE DELIVERY TARGETS AND OTHER PERFORMANCE INDICATORS (CONTINUE….)

DEPARTMENT:	CORPORATE SERVICES

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Vote | Project | Budget | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |
| Organisational Efficiency | Performance Management System | 150 000 | 0 | 150 000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Corporate Communication | 457 000 | 0 | 83 000 | 0 | 338 000 | 0 | 0 | 18 000 | 0 | 18 000 | 0 | 0 | 0 |
| External Funding | Policy Development | 1 500 000 | 0 | 375 000 | 0 | 375 000 | 0 | 0 | 375 000 | 0 | 375 000 | 0 | 0 | 0 |
|  | By-Laws Development | 500 000 | 0 |  | 0 | 180 000 | 0 | 0 | 320 00 | 0 |  | 0 | 0 | 0 |
| Corporate Support | Property Management | 7 520 069 | 0 | 1 607 017 | 0 | 2 702 017 | 0 | 0 | 2 362 017 | 0 | 2 362 017 | 0 | 0 | 0 |

DEPARTMENT:	Municipal Manager (Integrated Development Planning Unit)

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Vote | Project | Budget | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |
| CBP | Community Based Planning | 1 000 000 (external funding) |  | 500 000 | 250 000 | 250 000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| IDP Review | Analysis Phase | 40 000 | 0 | 0 | 40 000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Strategy Phase | 60 000 | 0 | 0 | 0 | 30 000 | 30 0000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Project Phase | 50 000 | 0 | 0 | 0 | 0 | 30 000 | 50 000 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Approval | 20 000 | 0 | 0 | 0 |  | 0 | 0 | 20 000 | 0 | 0 | 0 | 0 | 0 |
| IDP Implementation | Facilitation & Coordination | 500 000 (external funding) | 0 | 125 000 | 0 | 125 000 | 0 | 0 | 125 000 | 0 | 0 | 125 000 | 0 | 0 |
| Capacity Building/ Develop | IDP, Sector Plans/ Programmes | 600 000 (external funding) | 0 | 150 000 | 0 | 150 000 | 0 | 0 | 0 | 150 000 | 0 | 150 000 | 0 | 0 |
| Facilitation | Donor Funding Facilitation for IDP Projects | 5 000 000 (external funding) | 0 | 1 250 000 | 0 | 0 | 1 250 000 | 0 | 0 | 1 250 000 | 0 | 1 250 000 | 0 | 0 |

DEPARTMENT:	Land and Housing

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Vote | Project | Budget | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |
| Land & Accommodation | Land Release (5 000 target) | 4 542 (units) | 0 | 1 135 (units) | 0 | 1 135 (units) | 0 | 0 | 1 135 (units) | 0 | 0 | 1 137 (units) | 0 | 0 |
|  | Informal Settlement | 445 000 | 0 | 111 250 | 0 | 0 | 111 250 | 0 | 0 | 11 250 | 0 | 111 250 | 0 | 0 |
| Housing Dev | Housing Backlog 1000 units | 1 000 00 | 0 | 250 000 | 0 | 250 000 | 0 | 0 | 0 | 250 000 | 0 | 250 000 | 0 | 0 |
| Housing Admin | Customer Care |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Capacity Building | 100% | 0 | 25% | 0 | 25% | 0 | 0 | 0 | 25% | 0 | 25% | 0 | 0 |
|  | Policy Dev |  |  | 25% | 0 | 50% | 0 | 0 | 0 | 75% | 0 | 100% | 0 | 0 |
|  | Property Admin | 800 | 0 | 25% | 0 | 25% | 0 | 0 | 0 | 25% | 0 | 25% | 0 | 0 |
|  | Data Maintenance | 100% |  | 25% | 0 | 50% | 0 | 0 | 0 | 75% | 0 | 100% |  |  |

DEPARTMENT:	Local Economic Development (LED)

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Vote | Project | Budget | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |
| Marketing | Target Market enquiries | 80 000 | 0 | 20 000 | 0 | 20 000 | 0 | 0 | 20 000 | 0 | 20 000 | 0 | 0 | 0 |
|  | Investment & Tourism Hub promotion | 190 000 | 0 | 20 000 | 0 | 90 000 | 0 | 0 | 75 000 | 0 | 5 000 | 0 | 0 | 0 |
|  | Electronic Media Adverts | 80 000 | 0 | 10 000 | 0 | 40 000 | 0 | 0 | 20 000 | 0 | 20 000 | 0 | 0 | 0 |
| Tourism Development | Tourism Exhibitions | 75 000 | 0 | 38 000 | 0 | 15 000 | 0 | 0 |  | 15 000 | 0 | 7 000 | 0 | 0 |
| Tourism Promotion | Gateway Show | 47 000 | 0 | 47 000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Tourism Dev | Tourism Sector Plan Implementation | 940 000 | 0 | 350 000 | 0 | 270 000 | 0 | 0 | 300 000 | 0 | 40 000 | 0 | 0 | 0 |
| Policy Development | LED Strategy | 500 000 | 0 | 500 000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |

DEPARTMENT:	Local Economic Development (LED)   (Continue…..)

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Vote | Project | Budget | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |
| Policy Development | LED Strategy (external funding) | 3 500 000 | 0 | 875 000 | 0 | 875 000 | 0 | 0 | 857 000 | 0 | 0 | 875 000 | 0 | 0 |
| Policy Development | SMME Sector Plan | 500 000 | 0 | 0 | 200 000 |  | 300 000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Policy Development | Marketing Plan | 150 000 |  | 0 |  | 150 000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Policy Development | Agricultural Sector Plan | 250 000 | 0 | 0 | 0 | 250 000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |
| Policy Development | Retail Plan | (external funding) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Policy Development | Commercial/ Industrial Plan | (external funding) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Capacity Building | Slalom Canoe Dev Programme | 200 000 | 0 | 50 000 |  | 50 000 | 0 | 0 | 0 | 50 000 | 0 | 50 000 | 0 | 0 |
| LED Agriculture | Temo Land Care Project (Paul Roux) | 152 695 | 0 | 152 695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

DEPARTMENT:	Public Works

| Corporate Objective | Weighting | Key Performance Indicator | Annual Target | Quarterly Target |
| --- | --- | --- | --- | --- |
|  | PO | KPI |  |  | 1st | 2nd | 3rd | 4th |
| Provide Water |  |  | Number of Households provided with basic water Number of households provided with free basic water Review of the 2003 WSDP | 380 380 100 % | 40% | 380 380 60% |  |  |
| Provide Sanitation |  |  | Number of households provided with access to basic sanitation (VIP) Number of households provided with toilets (water borne system) | 1900 1420 | 500 400 | 1400 800 | 220 |  |
| Provide Electricity |  |  | Number of households provided with house connections Number of households provided with free basic electricity No. of new High mast erected No. of new street lights Registration with NERSA for licensing Implement the DSM | 550 11585 3 2240 | 240 | 1000 | 3 1000 |  |
| Maintain and Upgrade Road |  |  | Km of road upgraded and maintained gravel Km paved New km tarred Compile Terms Of Reference for the establishment of a Pavement Management System | 100 km 17 km 8 km 100% | 20 km 2 km | 25 km 5 km 50% | 35 km 8 km 2km 50% | 20 km 2 km 6 km |
| Provide Storm Water Management |  |  | Compile a Storm Water Management Plan Develop an Integrated Traffic Plan | 100% 100% |  | 25% | 35 % 50% | 40% 50% |
| Provide the Project Management Assistance in implantation of all projects |  |  | Implementation of 2003 Micro Software Project Reports to Council using MS Project Attend all MIG meetings Control and monitor all Projects – financial cash flows - Progress reports Compile BPs to access funding from various funders Compile and submit closed out reports for all MIG funded projects | 100% 4 12 12 15 5 | 50% 4 4 5 | 50% 4 4 5 3 | 2 4 4 5 2 | 2 |
| Promotion of stakeholder participation |  |  | Establish Technical forums Energy Forum Water Forum Roads and storm water Tech. Manager forum No. of Meetings with different stakeholders | 4 8 | 1 2 | 1 2 | 1 2 | 1 2 |
| Invest in Infrastructure |  |  | % of capital budget actually spent on capital projects % of operational budget spent on maintenance % of bids awarded to BEE Report on number of jobs created through LED initiatives including capital projects | 100% 100% 65% 500 | 15% | 30% | 40% | 15% |
| Enhance Customer Service |  |  | Conduct Customer Service Survey and report to MM | 100% | 10% | 60% | 20% |  |
| Improve Technology Efficiency |  |  | Develop an IT Strategy Implement the MS Project Upgrade and implement a user friendly GIS (reports to MM) | 100% 100% 100% | 20% | 50% 80% 45% | 50% 20% | 35% |
| Achieve Positive Employee Climate |  |  | Conduct an Employee Satisfaction Survey |  |  |  |  |  |
| Provision of plants and equipment |  |  | Develop a replacement and a disposal policy |  |  |  |  |  |

DEPARTMENT:	Finance (Detail see attached document)

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective | Measurable Objective | Annual Target |  |  |  |  |
| Financial Accounting | Compile Annual Financial Statements |  | 31/08/2007 |  |  |  |
| Financial Reporting | Management Responses to Audit Queries | Annual Report | 01/09/2007 | 30/11/2007 |  |  |
|  | Auditor General Report | Management Letter |  | 30/11/2007 |  |  |
|  | Corrected Journal Misallocation |  |  |  |  |  |
|  | Annual Report (Financial Statements) | Annual report at the end of financial year |  |  | 31/01/2008 |  |

DEPARTMENT:	Finance (Continue….)

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective | Measurable Objective | Annual Target |  |  |  |  |
| Financial Reporting | Implementation of GAMAP |  |  |  |  | 01/07/2008 |
|  | All related policies |  |  | 31/07/2007 |  |  |
|  | Investment Reconciliation | Monthly | Monthly | Monthly | Monthly | Monthly |
|  | Insurance Claims | Daily |  |  |  |  |
| Cost, Capital & Management Accounting | Review of established treasury budget office | Completed | 30/09/2007 |  |  |  |
| Budgeting and Budget Control | Compile municipal budget document aligned to IDP submitted to Council | December-May |  |  | 31/03/2008 |  |
|  | Compile Revised Budget | December-May |  |  | 31/03/2007 |  |
|  | Report on budget performance | Monthly | Monthly | Monthly | Monthly | Monthly |

DEPARTMENT:	Finance (Continue….)

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective | Measurable Objective | Annual Target |  |  |  |  |
| Cost, Capital & Management Accounting | Draft Adjustment Budget | January |  |  | 31/01/2008 |  |
|  | Draft new budget action plan | August | 31/08/2007 |  |  |  |
|  | Evaluated daily income and expenditure | Daily | Daily | Daily | Daily | Daily |
|  | Submit new budget to Council |  |  |  | 31/03/2008 |  |
|  | Section 71 monthly financial reports submitted to the Mayor | Monthly Reports | Monthly | Monthly | Monthly | Monthly |
| Cash Flow Management | Monthly cash flow projections inputs from directorates | Monthly | Monthly | Monthly | Monthly | Monthly |
|  | Monthly cash flow variance reports per department | Monthly | Monthly | Monthly | Monthly | Monthly |

DEPARTMENT:	Finance (Continue….)

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective | Measurable Objective | Annual Target |  |  |  |  |
| Cash Flow Management | Control of cash flow | Daily | Daily | Daily | Daily | Daily |
| Project Cost Accounting | Controlled expenditure on MIG projects and submitted reports to DPLG | Monthly | Monthly | Monthly | Monthly | Monthly |
| Grant Management | Financial System implemented | Once off |  |  |  |  |
|  | Internships employed |  | 01/07/2007 |  |  |  |
| Compensation of employees | Processed salaries on VIP Payroll system | Monthly | Monthly | Monthly | Monthly | Monthly |
|  | Accounts Payable to creditors/service providers | Monthly | Monthly | Monthly | Monthly | Monthly |

DEPARTMENT:	Finance (Continue….)

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective | Measurable Objective | Annual Target |  |  |  |  |
| Supply Chain Management | Revised current Supply Chain policy submitted to Council |  |  |  |  |  |
|  | Asset Register updated and compiled |  |  |  |  |  |
|  | Established Supply Chain committees |  |  |  |  |  |
|  | Updated database for service providers |  |  |  |  |  |
|  | No filled vacant post, officers, clerks |  |  |  |  |  |
|  | Number of in-house trained officials | 2 in-house training workshops |  |  |  |  |
|  | Number of externally trained officials | 2 external training workshops |  |  |  |  |

DEPARTMENT:	Finance (Continue….)

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective | Measurable Objective | Annual Target |  |  |  |  |
| Submission of reports | Compiled weekly reports to the CFO | Monthly report | Thursday/Week | Thursday/Week | Thursday/Week | Thursday/Week |
|  | Compiled monthly, quarterly and annual report to the Municipal Manager and Treasury. | End month | End month | End month | End month | End month |
| Asset registration management Submission of requisition books | Updated asset register report | End quarter | End quarter | End quarter | End quarter | End quarter |
| Stock counting | Controlled record of stock |  |  |  |  |  |
| Fixed Asset Management System | Recorded condition and value of fixed assets |  |  |  |  |  |

DEPARTMENT:	Finance (Continue….)

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective | Measurable Objective | Annual Target |  |  |  |  |
| Debt and Revenue Management | Accurate and optimum revenue collected |  |  |  |  |  |
| Rates Administration | Rates policy developed |  |  |  |  |  |
|  | Optimum revenue collected |  |  |  |  |  |
| Collection and management of revenue | Purified debtor data base and minimum debts in arrear |  |  |  |  |  |
| Managing of Debts and collection of arrears | Letters of demand sent Cutting-Off services Hand-over to Attorneys |  |  |  |  |  |
| Registering of Indigents | Number of indigents registered and updated |  |  |  |  |  |

DEPARTMENT:	Community Services

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Vote | Project | Budget | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |
| Nature and Environmental Admin | Maintenance of nature reserves and employment of staff | 930 123 |  | 232 351 |  | 232 351 |  |  | 232 351 |  |  | 232 351 |  |  |
| Parks & Recreation | Provision of facilities | 5 679 056 |  | 1 419 764 |  | 1 419 764 |  |  |  | 1 419 764 |  | 1 419 764 |  |  |
| Swimming pools | Provision of swimming pools | 273 783 |  | 684 446 |  | 684 446 |  |  | 684 446 |  |  | 684 446 |  |  |
| Protection services | Traffic Services | 3 374 081 |  | 843 520 |  | 843 520 |  |  | 843 520 |  |  | 843 520 |  |  |
|  | Disaster Management | 750 024 |  | 187 506 |  | 187 506 |  |  | 187 506 |  |  | 187 506 |  |  |
|  | Fire Brigade | 3 197 298 |  | 799 325 |  | 799 325 |  |  |  | 799 325 |  | 0 | 799 325 |  |
| Library | Library services | 1 711 801 |  | 427 950 |  | 427 950 |  |  | 427 950 |  |  | 427 950 | 0 |  |

DEPARTMENT:	Community Services (Continue….)

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Vote | Project | Budget | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |
| Waste management | Waste disposal, illegal dumping & street cleaning | 10 885 036 |  | 2 721 259 |  | 2 721 259 |  |  |  | 2 721 259 |  | 2 721 259 |  |  |
| Cemeteries | Control cemeteries | 1 353 547 |  | 338 387 |  | 338 387 |  |  | 338 387 |  |  | 338 387 |  |  |
| Sports Grounds | Availability of sport grounds | 2 413 401 |  | 603 350 |  | 603 350 |  |  | 603 350 |  |  | 603 350 |  |  |
| Pretorius Kloof | Upgrading and maintenance | 727 384 |  | 181 846 |  | 181 846 |  |  | 181 846 |  |  | 181 846 |  |  |
| Ikgatholleng Holiday Resort | Upgrading and maintenance | 58 505 |  | 14 626 |  | 14 626 |  |  | 14 626 |  |  | 14 626 |  |  |
| Administration | Effective Admin | 822 951 |  | 205 738 |  | 205 738 |  |  | 205 738 |  |  | 205 738 |  |  |

DEPARTMENT:	Office of the Speaker

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Vote | Project | Budget | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |
| Public Participation | Ward Committee training | 80 000 |  | 80 000 |  |  |  |  |  |  |  |  |  |  |
|  | Ward Committee and Community Development Workers sessions | 123 500 |  | 61 750 | 61 750 |  |  |  |  |  |  |  |  |  |
|  | Civil bodies workshop on governance | 150 000 |  |  |  |  | 150 000 |  |  |  |  |  |  |  |
| Capacity Building | Policy codes to be developed for councillors | 120 000 |  |  | 120 000 |  |  |  |  |  |  |  |  |  |

DEPARTMENT:	Office of the Speaker (Continue….)

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Vote | Project | Budget | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |
| Capacity Building | Workshop on new Policy Development | 60 000 |  | 15 000 |  | 15 000 |  |  |  | 15 000 |  | 15 000 |  |  |
|  | Woman’s month launch and summer held | 60 000 |  |  | 60 000 |  |  |  |  |  |  |  |  |  |
|  | Women Councillors to be trained on governance | 135 000 |  | 135 000 |  |  |  |  |  |  |  |  |  |  |
|  | Councillors to be trained on Legislation matters |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Community Based Planning | 1 000 000 (external funding) |  |  |  |  |  |  |  |  |  |  |  |  |

DEPARTMENT:	Office of the Mayor

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Vote | Project | Budget | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |
| Public Outreach |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Capacity Building |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Special Programmes | Youth Development |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Women Development |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Disability |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | HIV/AIDS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Inte-Governmental Relations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

DEPARTMENT:	Office of the Municipal Manager

|  |  |  | 1st Quarter | 2nd Quarter | 3rd Quarter | 4 Quarter |
| --- | --- | --- | --- | --- | --- | --- |
| Vote | Project | Budget | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |
| Effective Admin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Capacity Building |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Integrated Development Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance Management System |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political/ Admin Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Public Relations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Financial Viability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Internal Audit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institutional Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |