Draft proaramme for the PC SocDev: Sept -Nov 2007

Objective:

- To complete the Children's Amendment Bill, [CAB] B19B-2006 in this Parliamentary Year.

- To refer proposed amendments to the NCOP by 2 November 2007, as per NAPC recommendation on 13 September 2007

- To meet the Executive's request that will allow for implementation in the FY2008/09.

| Date | Activity | Role-players |
| --- | --- | --- |
| 14 Sept. 2007 | Notification and finalisation of oral presentations Comprehensive index of submissions received, oral, written, email, fax. | Committee Sec |
| 18 Sept 2007 09:0.0 -16:00 pm | Public hearings CAB | PC SocDev NGO's DSD |
| 18 Sept 2007 17:00 -18:00 pm | PC ManCom Draft PC prog - way fwd | Committee Sec Research Unit DSD PLO's |
| 19 Sept 2007 | Consideration of draft programme ' Deliberate public hearings. | PC SocDev DSD Research Unit |
| 21 Sept 2007 | Research reports completed, including hearings and scribe. Research reports distributed to PC SocDev | Research Unit Committee Sec Contract source for scribing of provincial hearings |
| 26-28 Sept 07 | Recess: Homework: Study submissions and | PC SocDev DSD + Legal team |
| 2-5 Oct 2007 | Special permission committee meetings in CT: 9-4 pm | PC SocDev, DSD, SLA, Research |
| 6-12 Oct 2007 To sit on each day marked as a committee including 8th Oct. No plenaries have been scheduled and the NAPC programme has been earmarked for committee work. Target full working committee days | Deliberations CAB Clause by clause Consider public inputs This is the make or break period! | PC SocDev DSD SLA Research |
| 17 Oct | Formal consideration of CAB, with amendments. Committee vote + report. | PC SocDev DSD SLA |
| 12-18 Oct 07 | SLA to verify bill and amendments SLA meeting L+P. | SLA DSD Request "C" printers proofs and review |
| 25 Oct 07 Second alternative date: 1 Nov 07 | NA debate on CAB, 2nd reading debate Consideration to MTBPS on | NA PC SocDev Executive |
|  | 30/10/07 and questions to Pres on 31 Oct 07 |  |
| Children's Amendment Bill, B19C-2006 is referred in time to NCOP for a 3 week cycle for consideration. NCOP to consider B 19D-2006. |
| 7 Nov 07 | Briefing: Regulations Children's Act, Sec 75 | PC SocDev DSD + Prof J Sloth-Nielsen |
| 14 Nov 07 | Briefing: Regulations to CAB, Sec 76 | PC SocDev DSD + Prof J Sloth Nielsen |
| 21 Nov 07 | Committee minutes for consideration | PC SocDev |